## Sayfa1
No | Reviewed Material ID | Section | Page | Line/ No | Error Type | Importance | Explanation | Correction Status | Correction Explanation
1 | G | Definitions | 3 | N/A | 9 | Little | Definitions and explanations are not clearly separated, it’s hard to read. | Corrected | Definitions and abbreviations are indicated in bold.
2 | I | 2. High-level (HL) objectives | 3 | 21-22-23 | 8 | Little | The followings are not listed in work items list ● Basic infrastructure of the backend side ● Generate ideas for Python-web interface ● Creation and approval for high level design ideas for architecture | Rejected | These are not specific works that specific manhours are allocated but rahter these are come up with in daily and weekly team meetings.
3 | I | 1. Key milestones | 3 | 4th record in the table | 6 | Medium | In the milestone "Initial version of the code - core features", core features are not clearly defined in neither this document nor work items list document | Corrected | Provide clear description of core features and list them concisely.
4 | P | 1 Project organization | 3 | 31 | 3 | Medium | Inconsistent team/unit/position names with respect to the stakeholders defined in Vision document (Section 3.1 Stakeholder Summary) | Corrected | Project plan updated to reflect/refer to Vision document.
5 | R | Risks | 2 | N/A | 9 | Little | Full text in cells are not visible until expanded. | Corrected | Pdf versions are to be uploaded to Github as well as .xls and/or .docx versions.
6 | R | Risks | 2 | 5 | 6 | Medium | Probability hasn't changed after mitigation. | Rejectted | Impact is changed, probability remains the same after mitigation.
7 | R | Risks | 2 | 7 | 4 | Medium | The mitigation of poor implementation is not correct. | Corrected | Poor development practices can be mitigated by promoting good CI practices, static code analysis, unit/functional and integration testing practices, peer review culture, etc.
8 | R | Risks | N/A | N/A | 9 | Important | Overloading the website your app is scraping with too many requests, can slow down the site or even cause it to crash. | Corrected | Risk added and relevant qualification/quantification performed.
9 | R | Risks | N/A | N/A | 9 | Important | Some websites have specific terms of service agreements that prohibit scraping | Corrected | Risk added and relevant qualification/quantification performed.
10 | R | Risks | N/A | N/A | 9 | Important | If the data in the website is not regularly updated, your app may extract inaccurate or outdated information | Corrected | Risk added and relevant qualification/quantification performed.
11 | S | 2. System-Wide Functional Requirements | 3 | 19 | 4 | Medium | None of the listed items are functional requirements. | Corrected | Majority of the requirements are corrected, reflecting use-case driven approach.
12 | S | 2. System-Wide Functional Requirements | 3 | 21 | 2 | Medium | Storing login information is for auditing purposes or regulatory compliance rather than ensuring user security. | Corrected | Requirement deleted.
13 | S | 2. System-Wide Functional Requirements | 3 | 23 | 3 | Medium | What is meant by "open-source licensing"? There are many types of open-source licensing where some restricts commercial usage. | Corrected | Requirement for commercial usage statement is added
14 | S | 2. System-Wide Functional Requirements | 3 | 34 | 3 | Little | Since an external authentication system is going to be used, why is this requirement listed here? | Corrected | The requirement is included in use cases and it is a requirement
15 | S | 2. System-Wide Functional Requirements | 3 | 36 | 2 | Little | Does ICTA act as a purchasing gateway, or does it provide any regulations for purchasing systems. | Corrected | The requirement is deleted to be further elaborated in the upcoming releases.
16 | S | 3.1. Usability | 4 | 41 | 7 | Important | Conflicts with UC1 | Corrected | Relevant section is updated to clear this ambiguity.
17 | S | 3.1. Usability | 4 | 41 | 7 | Important | Conflicts with UC1 | Corrected | Relevant section is updated to clear this ambiguity.
18 | S | 3.1. Usability | 4 | 44 | 3 | Little | Since this is basically an analysis system, what is meant by "..allow users to edit their order related information."? | Corrected | Order was intended to specify the products customers are interested in, i.e. order the system to birng out these products - the ambiguity is corrected.
19 | U | N/A | N/A | N/A | 9 | Medium | Overall styling inconsistencies across the document leading to confusion. | Corrected | All use cases were examined and deficiencies were corrected.
20 | U | N/A | N/A | N/A | 9 | Medium | Missing ToC - Table of Contents making it hard to jump to any use case | Corrected | Table of content page is added
21 | U | Use Case Model | 3 | 12 | 4 | Medium | Switching to a premium account does not have direct relation with an external Banking System actor. | Corrected | Banking system is added to the use case
22 | U | Use Case Model | 3 | 12 | 8 | Important | Missing “Subscribe” feature from the Vision document. | Corrected | Vision document is changed and it is handled in the UC1 as registration.
23 | U | Use Case Model | 3 | 12 | 8 | Important | Missing “Offline Usage” feature from the Vision document. | Corrected | Offline usage is removed from the vision document
24 | U | Use Case Model | 3 | 12 | 8 | Medium | Missing connection between the “Login to the system” UC and the external “Authentication System” actor. | Corrected | External Authentication System is removed from teh use case model and verification is made by the system itself.
25 | U | Use Case Model | 3 | 12 | 6 | Medium | Missing UC for premium users to downgrade their account. | Corrected | UC-5 is revised and it is added to the use case
26 | U | Use Case UC1: Register to System | 4 | 22 | 5 | Medium | Registration with only a username and password is inapplicable. If the username is intended to be the email, it must be stated explicitly in the “Special Requirements” section. | Corrected | UC-1 is revised
27 | U | Use Case UC1: Register to System | 4 | 23 | 1 | Little | Wrong usage of "user name" | Corrected | spelling mistake is corrected
28 | U | Use Case UC1: Register to System | 4 | 29 | 1 | Little | Grammatic error of “Standard” | Corrected | spelling mistake is corrected
29 | U | Use Case UC1: Register to System | 4 | 29 | 8 | Medium | The model describes an external authentication system actor, which is missing in primary actors. | Corrected | External Authentication System is removed from teh use case model and verification is made by the system itself.
30 | U | Use Case UC1: Register to System | 4 | 32 | 8 | Medium | "Main Success Scenario" header is missing. | Corrected | it is added.
31 | U | Use Case UC1: Register to System | 4 | 32 | 7 | Medium | No interaction described for the “Authentication System”. | Corrected | External Authentication System is removed from teh use case model and verification is made by the system itself.
32 | U | Use Case UC1: Register to System | 4 | 35 | 1 | Little | Wrong usage of "user name" | Corrected | spelling mistake is corrected
33 | U | Use Case UC1: Register to System | 4 | 39 | 8 | Little | Missing failure condition | Corrected | it is added to the use case
34 | U | Use Case UC1: Register to System | 4 | 44 | 8 | Medium |  | Corrected | use case is revised
35 | U | Use Case UC2: Log in to System | 4 | 53 | 1 | Little | Spelling error of “Standart” | Corrected | spelling mistake is corrected
36 | U | Use Case UC1: Register to System | 4 | 54 | 8 | Medium | "Main Success Scenario" header is missing. | Corrected | it is added to the use case
37 | U | Use Case UC1: Register to System | 4 | 61 | 8 | Medium | "Extensions" header is missing. | Corrected | it is added to the use case
38 | U | Use Case UC2: Log in to System | 4 | 61 | 6 | Medium | If the username was intended to be an email, how can a user forget her username and request it back from the system to her email? Otherwise, on UC-1, the email of the user was not requested during registration. | Corrected | UC2 is changed and the logic is corrected only password can be changed
39 | U | Use Case UC2: Log in to System | 4 | 61 | 3 | Medium | "User enters e-mail and clicks on log in." User should enter password too. | Corrected | it is added to the use case
40 | U | Use Case UC2: Log in to System | 4 | 64 | 1 | Little | Spelling error of “adress” | Corrected | spelling mistake is corrected
41 | U | Use Case UC2: Log in to System | 4 | 67 | 1 | Little | Wrong usage of "user users" | Corrected | spelling mistake is corrected
42 | U | Use Case UC3: Manage Personal Information | 5 | 82 | 1 | Little | Spelling error of “Standart” | Corrected | spelling mistake is corrected
43 | U | Use Case UC3: Manage Personal Information | 5 | 88 | 2 | Medium | Why are phone number and address information required? It is against the GDPR. | Corrected | it is added to the special requirements
44 | U | Use Case UC4: Manage Payment Information | 5 | 101 | 2 | Important | The use case does not cover PCI compliance which is a must for sensitive payment information. | Corrected | This is given in Vision document
45 | U | Use Case UC5: Switch Premium Account | 6 | 131 | 3 | Medium | It is not clear if the payment information is fetched from previously saved credit card, or the payment is completed ad-hoc. | Corrected | Use case is changed and it is stated that registered payment information is necessary
46 | U | Use Case UC5: Switch Premium Account | 6 | 139 | 6 | Medium | It should be stated in the preconditions that the credit card information is registered | Corrected | it is added to the use case
47 | U | Use Case UC6: Monitor Products | 7 | 163 | 5 | Medium | It is not practical to list products only by alphabetical order. There must be at least a category and seller filters. | Corrected | UC is changed.
48 | U | Use Case UC7: Manage Notification | 8 | 197 | 3 | Medium | Not clear full instruction set or the valid expressions of the instructions. | Corrected | UC is changed.
49 | U | Use Case UC8: Search Product | 8 | 224 | 3 | Medium | Not clear filtering options. | Corrected | UC is changed.
50 | U | Use Case UC8: Search Product | 9 | 241 | 3 | Medium | What if the product is not found? This extention should be added to use case. | Corrected | UC is changed.
51 | U | Use Case UC9: Manage Product | 9 | 247 | 3 | Medium | Not clear product attributes. | Corrected | UC is changed.
52 | U | Use Case UC9: Manage Product | 9 | 277 | 4 | Important | 2B.2c. describes update and remove actions, in this case the Extension does not apply for Remove operation. | Corrected | UC is changed.
53 | U | Use Case UC10: Request Support | 10 | 282 | 8 | Little | A support request generally requires a category. | Rejected | Category field is not necessary because user can select irrelevant category for their request so just taking the problem from user is enough for supporting
54 | U | Use Case UC11: View Historical Data | 10 | 304 | 8 | Medium | Missing time period constraint. | Corrected | UC is changed.
55 | U | Use Case UC12: Manage User Questions | 11 | 325 | 8 | Medium | A support request requires a status, otherwise it will not be clear if it is a pending request, or a new one, or a reply, or etc. | Corrected | UC is changed.
56 | U | Use Case UC12: Manage User Questions | 11 | 325 | 6 | Medium | UC-10 describes how to submit a "Support Request" but UC-12 describes how to answer "User Questions" which are basically different things. | Corrected | UC name is changed as Manage Support Requests
57 | U | Use Case UC13: Manage Users | 11 | 348 | 4 | Important | A normal user should only be onboarded through registration as described in UC1. | Corrected | UC is changed.
58 | U | Use Case UC14: Manage User Roles | 12 | 376 | 8 | Medium | Can a normal user be modified as a CSS for example? | Corrected | This use case is removed from the use case model and it is handled in UC-13
59 | U | Use Case UC1: Register to System | 4 | 29 | 6 | Important | "Premium User" is stated as one of the primary actors for this use case, but in order to be a "Premium User" from stratch there is no additional step or use case. | Corrected | Use case and use case model is changed. All users are standard at first and the use cases are revised according to this logic
60 | U | Use Case UC2: Log in to System | 4 | 68 | 8 | Little | Missing flow step | Corrected | UC is changed.
61 | U | Use Case UC4: Manage Payment Information | 5 | 107 | 6 | Medium | "Standard User" is stated as one of the primary actors for this use case. Since "Standard User" is assumed to be the ones with free subscription, there is no need for them to manage payment information. | Rejected | Both users can manage payment information. Because adding payment information is necessary for switchiing premium account or renew premium account at the end of the expiration date.
62 | U | Use Case UC5: Switch Premium Account | 6 | 141-148 | 8 | Medium | Missing the step of getting payment information from the user | Corrected | UC is changed.
63 | U | Use Case UC5: Switch Premium Account | 6 | 153 | 8 | Important | It is stated that there are 2 types of user, premium and standart. This use case describes to switch from standart to premium. So it is not clear that what options are provided and supposed to be selected in step 3a | Corrected | UC is changed.
64 | U | Use Case UC6: Monitor Products | 7 | 181 | 3 | Important | It is not clearly described in which scope these products are kept (in session or page) Also, In step "3a. User wants to remove products.", removal process is supposed to be clarified as well | Corrected | UC is changed.
65 | U | Use Case UC13: Manage Users | 11 | 348 | 8 | Important | The purpose of the use case is not understood. It is not clear which users the administrator manages and for what purpose | Corrected | UC is changed.
66 | U | Use Case UC14: Manage User Roles | 12 | 376 | 8 | Important | The purpose of the use case is not understood. It is not clear which user roles the administrator manages and for what purpose | Corrected | Use case is removed from the document and use case model.
67 | V | 2.1. Problem Statement | 3 | 22, 32 | 1 | Little | Comma needed after "However" | Corrected | "Howewer, " is used.
68 | V | 2.1. Problem Statement | 3 | 24 | 1 | Little | Comma needed after "e.g." | Corrected | "e.g.," is used.
69 | V | 2.1. Problem Statement | 3 | 38 | 1 | Little | Wrong usage of “can not” | Corrected | "cannot" is used.
70 | V | 2.1. Problem Statement | 3 | 39 | 1 | Little | Wrong usage of “can not” | Corrected | "cannot" is used.
71 | V | 2.1. Problem Statement | 3 | 22-30 | 3 | Medium | Too much detailed information which are not directly related with the problem | Rejected | It addresses all stakeholders and obeys the formats and customes of organizational project assets.
72 | V | 2.2. Product Position Statement | 5 | 53 | 1 | Little | Wrong usage of comma in "inflation, and" | Corrected | Corrected
73 | V | 2.2. Product Position Statement | 5 | 52-54 | 3 | Medium | The sentence is not clear "This software will also be used by sellers who claim to protect their customers against inflation, and give them the informed customer base they aspire to have. " | Corrected | Stement is revised and the sentence is broken down.
74 | V | 3.1.Stakeholder Summary | 6 | 71 | 1 | Little | "E-commerce platforms will offered to beta test the software" | Corrected | "E-commerce platforms will be offered to beta test the software." is used.
75 | V | 3.2. User Environment | 8 | 89 | 1 | Little | Wrong usage of “can not” | Corrected | "cannot" is used.
76 | V | 3.2. User Environment | 8 | 90 | 1 | Little | Wrong usage of “can not” | Corrected | "cannot" is used.
77 | V | 3.2. User Environment | 8 | 89-90 | 3 | Medium | The sentence is not clear "The web scraping activities can not be used in any area/vehicle restraining data transfer as web scraping can not be performed. However offline use will be available." | Corrected | Stement is revised.
78 | V | 4.1. Needs and Features | 8 | 95 | 8 | Important | In the "Product Position Statement" it is clearly stated that the proposed solution "is a web scraping and analysis tool". Though, there aren't any needs or features described either for web scraping nor analysis. | Corrected | Relevant needs are added.
79 | V | 4.1. Needs and Features | 8 | 95 | 8 | Important | Are the features stated as to be released in release 1.0, planned for all users?(consumers, sellers, ecommerce platforms) | Corrected | Added statement "Please note that “users” refer to consumers, sellers, and e-commerce platforms".
80 | V | 4.1. Needs and Features | 9 | 95 | 9 | Little | Since the features are not grouped in order of releases, it is difficult to track while reading. | Corrected | Featurea are grouped in the order of releases (ascending release no).
81 | V | 4.1. Needs and Features | 9 | 95 | 8 | Important | The feature "Users can use offline features, downloaded files and so on" is not explicitly defined. | Corrected | Offline features are elaborated.
82 | W | WIL_Iteration_1 | N/A | N/A | 8 | Important | Work items are missing. | Corrected | All work items for itearations are added.
a | b | c | d | e | f | g | h | i | j