## Sayfa1
No | Reviewed Material ID | Section | Page | Line/ No | Error Type | Importance | Explanation | Accepted | Correction Explanation
1 | A | 2. Architectural goals and philosophy | 1 | 9 | 8 | Medium | No solid goals were defined nor a set of philosophies were formulated to address these goals. | To be performed in Iteration 3
2 | A | 3. Assumptions and dependencies | 1 | 14 | 8 | Little | Assumptions and dependencies are not properly listed. | To be performed in Iteration 3
3 | A | 4. Architecturally significant requirements | 1 | 20 | 4 | Medium | Links or references from the Vision, Use Cases or SWRS are not provided. | To be performed in Iteration 3
4 | A | 5. Decisions, constraints, and justifications | 1 | 24 | 4 | Important | Justifications and possible alternatives are not provided. | To be performed in Iteration 3
5 | A | 6. Architectural Mechanisms | 1 | 36 | 4 | Important | Architectural mechanisms are not properly provided. | To be performed in Iteration 3
6 | A | 7. Key abstractions | 1 | 41 | 4 | Important | Key abstractions are not properly provided neither by list or model. | To be performed in Iteration 3
7 | A | 8. Layers or architectural framework | 2 | 46 | 4 | Medium | Neither layers or architectural framework are properly described. | To be performed in Iteration 3
8 | A | 9. Architectural views | 2 | 52 | 8 | Medium | The provided diagram is vague and does not explain much. | To be performed in Iteration 3
9 | A | 9. Architectural views | 2 | 52 | 6 | Important | The provided diagram does not comply with the MVC model as it is missing the Model and View parts. | To be performed in Iteration 3
10 | D | N/A | 1 | 1 | 9 | Medium | The document does not have a version history, headers and footers, ToC, cover page, etc. | To be performed in Iteration 3
11 | D | Subsystems | 2 | 14 | 8 | Medium | Couldn't get the point why an extra entity as PriceSource is required. | To be performed in Iteration 3
12 | D | Requirement Realization | 2 | 25 | 6 | Important | Use cases assigned in the Work Item List (UC-2, UC-6 and UC-8) are missing | To be performed in Iteration 3
13 | D | Requirement Realization | 2 | 25 | 2 | Important | The sequence diagrams does not comply with the OAuth2.0 protocol which is defined as the security measure for user authentication in the SWRS document. | To be performed in Iteration 3
14 | D | Requirement Realization | 3 | 32 | 8 | Medium | Couldn't get which UC the Confirmation Process refers to. | To be performed in Iteration 3
15 | TC | N/A | 1 | 1 | 6 | Medium | Use cases assigned in the Work Item List (UC-6 and UC-8) are missing | To be performed in Iteration 3 | Note: The 2 UC's are detailed per the assumption that 2 test cases are to be deteailed
16 | TS | N/A | 1 | 1 | 6 | Medium | Use cases assigned in the Work Item List (UC-6 and UC-8) are missing | To be performed in Iteration 3 | Note: The 2 UC's are detailed per the assumption that 2 test cases are to be deteailed
17 | I | N/A | N/A | N/A | 2 | Little | Pushing each document with a version number makes it difficult to track documents. Instead, using version history in the documents is enough. | Rejected | The latest versions of the documents are to be pushed and uploaded for convenience
18 | I | 1.Key Milestones | 3 | 17 | 6 | Medium | Although UC-5, UC-3, UC-4, UC-9, UC-7 are provided in this table, their status are still "In Backlog" in Work Items List document. | Accepted | Corrected as "assigned"
19 | I | 3. Work Item Assignments | 3 | 26 | 4 | Little | Although it is the plan or iteration 3, the statement is provided for iteration 2. | Accepted | Corrected as required.
20 | TS | Test steps | N/A | N/A | 9 | Little | It would be more accurate to write test steps in the form of orders. | Accepted | The steps are rephrased.
21 | TS | Test steps | N/A | N/A | 3 | Important | Test steps should be more clear. For example the data used while testing must be stated. Tests should be able to be run without interruption. | Rejected - accepted the convention for steps as above | The steps are rephrased.
22 | W | N/A | 1 | N/A | 8 | Important | There is no work item assigned for iteration 3. Hence, it is not understood that which of these are planned to be included for iteration 3. | Accepted | Corrected as "assigned"
23 | U | UC-4 (Manage Payment Information) | 5 | 1 | 3 | Medium | Standart user is stated as one of the primary actors. It is not clear that why this user manages payment since this type of user is assumed to be free. | To be performed in Iteration 3
24 | TC | N/A | N/A | N/A | 8 | Medium | It is stated in work items list, and iteration plan 2 that UC-1, UC-2, UC-6, UC-8 are implemented, however test cases for UC-8 and UC-9 are neither exist nor planned. | To be performed in Iteration 3 | Note: The 2 UC's are detailed per the assumption that 2 test cases are to be deteailed