## Sheet1
Name / Description | Priority | Size estimate (Points) | State | Target iteration | Assigned To | Effort estimate left (hours) | Hours worked | Reference material
Produce initial glossary | 1 | 1 | Closed | 1 | Murat-Tolga-İsmail-Taylan | 0 | 2 | version 1.0 glossary document
Produce initial vision | 1 | 5 | Closed | 1 | Murat-Tolga-İsmail-Taylan | 0 | 20 | version 1.0 vision document
Produce initial system-wide requirements | 1 | 2 | Closed | 1 | Murat-Tolga-İsmail-Taylan | 0 | 5 | version 1.0 system-wide requirements
Produce initial use case model and use cases | 1 | 5 | Closed | 1 | Murat-Tolga-İsmail-Taylan | 0 | 20 | version 1.0 use case model and use cases
Produce initial risk list | 1 | 1 | Closed | 1 | Murat-Tolga-İsmail-Taylan | 0 | 2 | version 1.0 risk list
Produce initial work items list | 1 | 1 | Closed | 1 | Murat-Tolga-İsmail-Taylan | 0 | 2 | version 1.0 work items list
Produce iteration plan for iterations 1&2 | 1 | 3 | Closed | 1 | Murat-Tolga-İsmail-Taylan | 0 | 10 | version 1.0 iteration plan for iterations 1&2
Produce initial project plan | 1 | 3 | Closed | 1 | Murat-Tolga-İsmail-Taylan | 0 | 10 | version 1.0 project plan
Finalize vision | 1 | 1 | Closed | 1 | Murat-Tolga-İsmail-Taylan | 0 | 2 | version 1.1 vision document
Update glossary | 5 | 1 | Closed | 2 | Murat-Tolga-İsmail-Taylan | 0 | 2 | glossary document
Update work items list | 5 | 1 | Closed | 2 | Murat-Tolga-İsmail-Taylan | 0 | 2 | work items list document
Produce iteration plan for iteration 3 | 2 | 2 | Closed | 2 | Murat-Tolga-İsmail-Taylan | 0 | 4 | iteration plan document
Update project plan | 2 | 1 | Closed | 2 | Murat-Tolga-İsmail-Taylan | 0 | 2 | project plan document
Update risk list | 3 | 1 | Closed | 2 | Murat-Tolga-İsmail-Taylan | 0 | 2 | risk list document
Update system-wide requirements | 3 | 1 | Closed | 2 | Murat-Tolga-İsmail-Taylan | 0 | 2 | system-wide requirements document
Update use cases and use case model | 3 | 2 | Closed | 2 | Murat-Tolga-İsmail-Taylan | 0 | 4 | use case model and use cases document
Generalize the infrastructure of the software | 1 | 5 | Closed | 2 | Murat-Tolga-İsmail-Taylan | 0 | 20
Produce initial architecture notebook | 1 | 3 | Closed | 2 | Murat-Tolga-İsmail-Taylan | 0 | 10 | architecture notebook document
Implementation of UC-1 "Register to the System" | 1 | 8 | Closed | 2 | Murat-Tolga-İsmail-Taylan | 0 | 45 | UC-1 "Register to the System" in the use case document
** Prototype UI |  |  | Closed | 2 | Murat-Tolga-İsmail-Taylan
** Design and perform related documentation |  |  | Closed | 2 | Murat-Tolga-İsmail-Taylan
** Implement and test and perform related documentation |  |  | Closed | 2 | Murat-Tolga-İsmail-Taylan
Implementation of UC-2 "Login to the System" | 1 | 8 | Closed | 2 | Murat-Tolga-İsmail-Taylan | 0 | 45 | UC-2 "Login to the System" in the use case document
** Prototype UI |  |  | Closed | 2 | Murat-Tolga-İsmail-Taylan
** Design and perform related documentation |  |  | Closed | 2 | Murat-Tolga-İsmail-Taylan
** Implement and test and perform related documentation |  |  | Closed | 2 | Murat-Tolga-İsmail-Taylan
Implementation of UC-6 "Monitor Products" | 1 | 8 | Closed | 2 | Murat-Tolga-İsmail-Taylan | 0 | 45 | UC-6 "Monitor Products" in the use case document
** Prototype UI |  |  | Closed | 2 | Murat-Tolga-İsmail-Taylan
** Design and perform related documentation |  |  | Closed | 2 | Murat-Tolga-İsmail-Taylan
** Implement and test and perform related documentation |  |  | Closed | 2 | Murat-Tolga-İsmail-Taylan
Implementation of UC-8 "Search Products" | 1 | 8 | Closed | 2 | Murat-Tolga-İsmail-Taylan | 0 | 45 | UC-8 "Search Products" in the use case document
** Prototype UI |  |  | Closed | 2 | Murat-Tolga-İsmail-Taylan
** Design and perform related documentation |  |  | Closed | 2 | Murat-Tolga-İsmail-Taylan
** Implement and test and perform related documentation |  |  | Closed | 2 | Murat-Tolga-İsmail-Taylan
Perform Configuration Management (CM) Related Operations (Revision Control, Release Notes, Baselines etc.) | 2 | 1 | Closed | 2 | Murat-Tolga-İsmail-Taylan | 0 | 2
Perform Quality Assurance (QA) Related Operations (Document Reviews, Functional and System Tests etc.) | 2 | 2 | Closed | 2 | Murat-Tolga-İsmail-Taylan | 0 | 4
Produce test cases for UC-1, UC-2, UC-6, UC-8 and do tests and produce test logs | 2 | 5 | Closed | 2 | Murat-Tolga-İsmail-Taylan | 0 | 20 | test case documents
Update glossary | 5 | 1 | Closed | 3 | Murat-Tolga-İsmail-Taylan | 0 | 2 | glossary document
Update work items list | 5 | 1 | Closed | 3 | Murat-Tolga-İsmail-Taylan | 0 | 2 | work items list document
Produce iteration plan for iteration 4 | 2 | 2 | Closed | 3 | Murat-Tolga-İsmail-Taylan | 0 | 4 | iteration plan document
Update project plan | 2 | 1 | Closed | 3 | Murat-Tolga-İsmail-Taylan | 0 | 2 | project plan document
Update risk list | 3 | 1 | Closed | 3 | Murat-Tolga-İsmail-Taylan | 0 | 2 | risk list document
Update system-wide requirements | 3 | 1 | Closed | 3 | Murat-Tolga-İsmail-Taylan | 0 | 2 | system-wide requirements document
Update use cases and use case model | 3 | 2 | Closed | 3 | Murat-Tolga-İsmail-Taylan | 0 | 4 | use case model and use cases document
Update architecture notebook | 2 | 1 | Closed | 3 | Murat-Tolga-İsmail-Taylan | 0 | 2 | architecture notebook document
Implementation of UC-5 "Manage Account" | 1 | 8 | Closed | 3 | Murat-Tolga-İsmail-Taylan | 0 | 45 | UC-5 "Manage Account" in the use case document
** Prototype UI |  |  | Closed | 3 | Murat-Tolga-İsmail-Taylan
** Design and perform related documentation |  |  | Closed | 3 | Murat-Tolga-İsmail-Taylan
** Implement and test and perform related documentation |  |  | Closed | 3 | Murat-Tolga-İsmail-Taylan
Implementation of UC-3 "Manage Personal Information" | 1 | 8 | Closed | 3 | Murat-Tolga-İsmail-Taylan | 0 | 45 | UC-3 "Manage Personal Information" in the use case document
** Prototype UI |  |  | Closed | 3 | Murat-Tolga-İsmail-Taylan
** Design and perform related documentation |  |  | Closed | 3 | Murat-Tolga-İsmail-Taylan
** Implement and test and perform related documentation |  |  | Closed | 3 | Murat-Tolga-İsmail-Taylan
Implementation of UC-4 "Manage Payment Information" | 1 | 8 | Closed | 3 | Murat-Tolga-İsmail-Taylan | 0 | 45 | UC-4 "Manage Payment Information" in the use case document
** Prototype UI |  |  | Closed | 3 | Murat-Tolga-İsmail-Taylan
** Design and perform related documentation |  |  | Closed | 3 | Murat-Tolga-İsmail-Taylan
** Implement and test and perform related documentation |  |  | Closed | 3 | Murat-Tolga-İsmail-Taylan
Implementation of UC-9 "Manage Products" | 1 | 8 | Closed | 3 | Murat-Tolga-İsmail-Taylan | 0 | 45 | UC-9 "Manage Products" in the use case document
** Prototype UI |  |  | Closed | 3 | Murat-Tolga-İsmail-Taylan
** Design and perform related documentation |  |  | Closed | 3 | Murat-Tolga-İsmail-Taylan
** Implement and test and perform related documentation |  |  | Closed | 3 | Murat-Tolga-İsmail-Taylan
Implementation of UC-7 "Manage Notification" | 1 | 8 | Closed | 3 | Murat-Tolga-İsmail-Taylan | 45 | 45 | UC-7 "Manage Notification" in the use case document
** Prototype UI |  |  | Closed | 3 | Murat-Tolga-İsmail-Taylan
** Design and perform related documentation |  |  | Closed | 3 | Murat-Tolga-İsmail-Taylan
** Implement and test and perform related documentation |  |  | Closed | 3 | Murat-Tolga-İsmail-Taylan
Perform Configuration Management (CM) Related Operations (Revision Control, Release Notes, Baselines etc.) | 2 | 1 | Closed | 3 | Murat-Tolga-İsmail-Taylan | 0 | 2
Perform Quality Assurance (QA) Related Operations (Document Reviews, Functional and System Tests etc.) | 2 | 2 | Closed | 3 | Murat-Tolga-İsmail-Taylan | 0 | 4
Produce test cases for UC-3, UC-4, UC-5, UC-7, UC-9 and do tests and produce test logs | 2 | 5 | Closed | 3 | Murat-Tolga-İsmail-Taylan | 0 | 20 | test case documents
Finalize glossary | 5 | 1 | Closed | 4 | Murat-Tolga-İsmail-Taylan | 2 |  | glossary document
Finalize work items list | 5 | 1 | Closed | 4 | Murat-Tolga-İsmail-Taylan | 2 |  | work items list document
Finalize project plan | 2 | 2 | Closed | 4 | Murat-Tolga-İsmail-Taylan | 4 |  | project plan document
Finalize risk list | 2 | 1 | Closed | 4 | Murat-Tolga-İsmail-Taylan | 2 |  | risk list document
Finalize system-wide requirements | 2 | 1 | Closed | 4 | Murat-Tolga-İsmail-Taylan | 2 |  | system-wide requirements document
Finalize use cases and use case model | 2 | 2 | Closed | 4 | Murat-Tolga-İsmail-Taylan | 4 |  | use case model and use cases document
Finalize architecture notebook | 2 | 2 | Closed | 4 | Murat-Tolga-İsmail-Taylan | 4 |  | architecture notebook document
Implementation of UC-11 "View Historical Data" | 1 | 8 | Closed | 4 | Murat-Tolga-İsmail-Taylan | 45 |  | UC-11 "View Historical Data" in the use case document
** Prototype UI |  |  | Closed | 4 | Murat-Tolga-İsmail-Taylan
** Design and perform related documentation |  |  | Closed | 4 | Murat-Tolga-İsmail-Taylan
** Implement and test and perform related documentation |  |  | Closed | 4 | Murat-Tolga-İsmail-Taylan
Implementation of UC-10 "Request Support" | 1 | 8 | Closed | 4 | Murat-Tolga-İsmail-Taylan | 45 |  | UC-10 "Request Support" in the use case document
** Prototype UI |  |  | Closed | 4 | Murat-Tolga-İsmail-Taylan
** Design and perform related documentation |  |  | Closed | 4 | Murat-Tolga-İsmail-Taylan
** Implement and test and perform related documentation |  |  | Closed | 4 | Murat-Tolga-İsmail-Taylan
Implementation of UC-12 "Manage Support Requests" | 1 | 8 | Closed | 4 | Murat-Tolga-İsmail-Taylan | 45 |  | UC-12 "Manage Support Requests" in the use case document
** Prototype UI |  |  | Closed | 4 | Murat-Tolga-İsmail-Taylan
** Design and perform related documentation |  |  | Closed | 4 | Murat-Tolga-İsmail-Taylan
** Implement and test and perform related documentation |  |  | Closed | 4 | Murat-Tolga-İsmail-Taylan
Implementation of UC-13 "Manage Users" | 1 | 8 | Closed | 4 | Murat-Tolga-İsmail-Taylan | 45 |  | UC-13 "Manage Users" in the use case document
** Prototype UI |  |  | Closed | 4 | Murat-Tolga-İsmail-Taylan
** Design and perform related documentation |  |  | Closed | 4 | Murat-Tolga-İsmail-Taylan
** Implement and test and perform related documentation |  |  | Closed | 4 | Murat-Tolga-İsmail-Taylan
Implementation of UC-7 "Manage Notification" | 1 | 8 | Closed | 3 | Murat-Tolga-İsmail-Taylan | 45 |  | UC-7 "Manage Notification" in the use case document
** Prototype UI |  |  | Closed | 3 | Murat-Tolga-İsmail-Taylan
** Design and perform related documentation |  |  | Closed | 3 | Murat-Tolga-İsmail-Taylan
** Implement and test and perform related documentation |  |  | Closed | 3 | Murat-Tolga-İsmail-Taylan
Perform Configuration Management (CM) Related Operations (Revision Control, Release Notes, Baselines etc.) | 2 | 1 | Closed | 4 | Murat-Tolga-İsmail-Taylan | 2
Perform Quality Assurance (QA) Related Operations (Document Reviews, Functional and System Tests etc.) | 2 | 2 | Closed | 4 | Murat-Tolga-İsmail-Taylan | 4
Produce test cases for UC-10, UC-11, UC-12, UC-13 and do tests and produce test logs | 2 | 5 | Closed | 4 | Murat-Tolga-İsmail-Taylan | 20 |  | test case documents
Perform a lessons learned session for first release and produce document to improve future project performance | 1 | Not planned | In Backlog | 5 | Murat-Tolga-İsmail-Taylan | Not planned
Operation and maintenance and any other transition activities after the first major release, i.e., after the deployment of the project at the end of Iteration 4 | 1 | Not planned | In Backlog | 5 | Murat-Tolga-İsmail-Taylan | Not planned
Documentation, Design, Implementation, Deployment and any other activities after the first release that are mentioned in the Vision Document | 1 | Not planned | In Backlog | 5 | Murat-Tolga-İsmail-Taylan | Not planned