## Revision_history
Date | Version | Type | Description | Prepared by | Checked by
2023-03-30 | 1.0 | IFC | Preliminary draft | IMT2 Dev | IMT2 QA/QC

## Risks
AnyChange Risk List
Risk ID | Date Identified | Headline | Description | Type | Impact | Probability | Magnitude | Owner | Risk Response | Impact after mitigation | Probability after mitigation | Magnitude after mitigation
1 | 30.03.2023 | Communication errors | Lack of communication / miscommunication between team members resulting in incompatible artifacts and product, quality issues, and so on | Management | 4 | 80% | 3.2 | PM | Mitigation: Daily communication - minimum once every two days - is being performed Informal communication encouraged, formal communication only required for responsiblity sharing per RACI charts | 3 | 20% | 0.6
2 | 30.03.2023 | Non-compliance with GDPR | User information for user settings, login, registration etc may not comply with relevant GDPR policies leading to legal actions against the company and so on | Business | 5 | 40% | 2 | PM | Mitigation: Get consultancy from legal department | 4 | 10% | 0.4
3 | 30.03.2023 | Change of stakeholder requirements | Change of requirements resulting in a software that does not meet the new demands may lead to incompliance per business goals | Business | 5 | 90% | 4.5 | Team | Mitigation: Involve stakeholders to communication cycle | 1 | 90% | 0.9
4 | 30.03.2023 | Estimation mistakes | Mistakes in scope, cost, schedule estimations may lead to overbudget, overtime and so on | Management | 4 | 50% | 2 | PM | Mitigation: Adopt UP for incremental iterative development | 2 | 40% | 0.8
5 | 30.03.2023 | Unavailability of resources due to sickness, family reasons, force-majeure | Resources (manpower, equipment, and so on) not being available due to both foreseeable and unforeseeable events may lead to a massive decrease project performance parameters (cost, schedule, quality, scope) | Resource | 4 | 50% | 2 | Team | Mitigation Project sponsor dedicating additional backup resources Descoping in one iteration and taking up in the next Transfer Private health insurance is being supplied to employees for securing faster recovery | 2 | 40% | 0.8
6 | 30.03.2023 | Overdesign | Development of the software not only to the requirements but also nice-to-haves not specifically declared and agreed upon by stakeholders | Management | 3 | 35% | 1.05 | Team | Mitigation Enhance stakeholder communication Use iteration planning based on must-haves and nice-to-haves Ensure requirements are agreed upon | 2 | 10% | 0.2
7 | 30.03.2023 | Poor implementation of design | Development not being made per archtiecture and hence primary design decisions may lead to bad design and incompliance with stakeholder requirements | Technical | 4 | 25% | 1 | Team | Mitigation Use UP, architecture notebook Update architecture if design change is approved by team, stakeholders / management Use good communication practices per UP | 3 | 20% | 0.6
8 | 30.03.2023 | Lack of security, vulnerability to attacks | Malicious attacks to take down the platform may lead to downtime, user information theft and so on further leading to legal actions against the company | Technical | 5 | 20% | 1 | PM | Mitigation Get consultancy and services from cybersecurity companies | 5 | 1% | 0.05
9 | 30.03.2023 | IP theft | Company being accused of IP theft or being subjected to IP theft may lead to incompliance with business practices, loss of reputation etc | Business | 4 | 25% | 1 | PM | Mitigation Get consultancy and services from cybersecurity companies Thorough research of IPs before development and ensuring development does not interfere with those | 4 | 3% | 0.12
10 | 30.03.2023 | Browser incompatibility | Platform not working correctly on all browsers / malfunctioning in some browsers | Technical | 4 | 30% | 1.2 | Team | Mitigation Ensure browser-agnostic development | 4 | 5% | 0.2

## Quantitative_risk_analysis_matr
Magnitude | Category | Description | Response
<1 | Riskfree | No risk | Accept
>=1 | Less risky | Acceptable risk | Avoid, mitigate, transfer, accept
>=2 | Risky | Risk reduction required (3rd) | Avoid, mitigate, transfer
>=3 | Hazardous | Risk reduction required (2nd) | Avoid, mitigate, transfer
>=4 | Fatal | Risk reduction required ASAP (1st) | Avoid, mitigate, transfer